## Submittal Log
Submittal_Number | Spec_Section | Description | Submitted_Product | Manufacturer | Status | Reviewer | Date_Submitted | Date_Reviewed | Notes
SC-001 | 07 42 13 | Terracotta Rainscreen Panels - Primary Field | Alphaton Series 400 Warm Sienna S-482 | Moeding | Approved | Marco Vitale | 2025-03-01 | 2025-03-08 | Basis of design product. Color approved.
SC-002 | 07 42 13 | Terracotta Rainscreen Panels - Accent Band | Alphaton Series 400 Sand Beige S-310 | Moeding | Approved | Marco Vitale | 2025-03-01 | 2025-03-08 | Basis of design product. Color approved.
SC-003 | 07 42 13 | Rainscreen Substructure System | Alphaton AG-500 Aluminum Rail System | Moeding | Approved | Marco Vitale | 2025-03-05 | 2025-03-14 | Wind load calculations verified for HVHZ.
SC-004 | 07 42 13 | Terracotta Corner Panels | Custom mitered corners - Alphaton | Moeding | Pending | Marco Vitale | 2025-03-20 |  | Awaiting shop drawing with corner detail dimensions.
SC-005 | 07 42 13 | Cavity Fire Stops | Thermafiber Mineral Wool Curtain Wall Insulation | Owens Corning | Approved | Marco Vitale | 2025-03-10 | 2025-03-17 | Complies with NFPA 285 and cavity fire stop requirements.
SC-006 | 08 71 00 | Residential Unit Entry Locksets | L-Series L9453 Mortise Lock - 626 finish | Schlage | Approved | Akshay Mehra | 2025-03-03 | 2025-03-10 | Basis of design. Keying schedule pending.
SC-007 | 08 71 00 | Stairwell Door Hardware Set | L-Series L9080 + BB1279 hinges + 4040XP closer | Schlage/Hager/LCN | Approved | Akshay Mehra | 2025-03-03 | 2025-03-10 | UL listing confirmed for 90-min fire rating.
SC-008 | 08 71 00 | Common Area Locksets | L-Series L9456 Entrance Function - 626 finish | Schlage | Revise & Resubmit | Akshay Mehra | 2025-03-03 | 2025-03-12 | Finish does not match spec. Submitted 625 (bright chrome) instead of 626 (satin chrome). Resubmit with correct finish.
SC-009 | 08 71 00 | Door Closers - Mechanical Rooms | 4041 Series surface closer | LCN | Revise & Resubmit | Akshay Mehra | 2025-03-05 | 2025-03-14 | Spec requires 4040XP series. 4041 does not have parallel arm option required for narrow frame condition. Resubmit.
SC-010 | 22 40 00 | Water Closets - Residential Units | Aquia IV Dual Flush - Cotton White | Toto | Approved | Sarah Kim | 2025-03-08 | 2025-03-15 | Basis of design. WaterSense certified confirmed.
SC-011 | 22 40 00 | Lavatories - Residential Units | Vox Rectangle Vessel - White | Kohler | Approved | Sarah Kim | 2025-03-08 | 2025-03-15 | Basis of design product.
SC-012 | 22 40 00 | Bathtubs - Standard Units | Underscore Rectangle 60x30 - White | Kohler | Approved | Sarah Kim | 2025-03-08 | 2025-03-15 | Left-hand drain confirmed per unit layouts.
SC-013 | 22 40 00 | Bathtubs - Three-Bedroom Premium Units | BetteLux Oval Silhouette freestanding | Bette | Revise & Resubmit | Sarah Kim | 2025-03-10 | 2025-03-18 | Spec requires Kohler Ceric in Lithocast material. Submitted Bette product is steel/enamel, different material and smaller dimensions (63" vs spec 65"). Resubmit with specified product or equal in Lithocast/solid surface.
SC-014 | 22 40 00 | Kitchen Sinks - Residential Units | Precis 30" Single Bowl - Metallic Gray | Blanco | Approved | Sarah Kim | 2025-03-08 | 2025-03-15 | Basis of design. Accessories included.
SC-015 | 22 40 00 | Bathroom Faucets | Essence Widespread - SuperSteel finish | Grohe | Approved | Sarah Kim | 2025-03-12 | 2025-03-19 | WaterSense certified. 1.2 GPM confirmed.
SC-016 | 22 40 00 | Kitchen Faucets | Minta Pull-Down Spray - Chrome finish | Grohe | Revise & Resubmit | Sarah Kim | 2025-03-12 | 2025-03-19 | Spec requires Ladylux model in Brushed Nickel (SuperSteel). Submitted Minta in Chrome. Wrong model and wrong finish. Resubmit.
SC-017 | 22 40 00 | Showerheads - Rainshower | Rainshower Cosmopolitan 310 - SuperSteel | Grohe | Approved | Sarah Kim | 2025-03-12 | 2025-03-19 | 12" ceiling mount confirmed. 2.0 GPM.
SC-018 | 22 40 00 | Shower Valves | GrohFlex Universal Rough-In Valve | Grohe | Rejected | Sarah Kim | 2025-03-14 | 2025-03-21 | Spec requires Grohtherm SmartControl thermostatic valve. GrohFlex is a pressure-balance valve, not thermostatic. Does not meet specification. Resubmit with correct product.
SC-019 | 07 42 13 | Terracotta Panel - NOA Documentation | Florida Product Approval #FL-38291 | Moeding | Approved | Keith Sagliocca | 2025-03-18 | 2025-03-25 | HVHZ compliant. Valid through 2027.
SC-020 | 08 44 00 | Curtain Wall System - Impact Windows | Kawneer 1600UT System 2 | Kawneer | Pending | Marco Vitale | 2025-03-22 |  | NOA documentation under review. Impact testing report received. Wind load calc pending.