## Monthly Financials
Month | Revenue | Expenses | Net Profit | Profit Margin | Projects Active | New Commissions | Staff Count | Utilization Rate
2025-01-01 | 425000 | 375000 | 50000 | 11.76% | 9 | 2 | 24 | 72%
2025-02-01 | 440000 | 380000 | 60000 | 13.64% | 10 | 1 | 24 | 74%
2025-03-01 | 485000 | 395000 | 90000 | 18.56% | 11 | 3 | 25 | 78%
2025-04-01 | 520000 | 410000 | 110000 | 21.15% | 12 | 2 | 25 | 80%
2025-05-01 | 545000 | 425000 | 120000 | 22.02% | 13 | 2 | 26 | 82%
2025-06-01 | 490000 | 415000 | 75000 | 15.31% | 12 | 1 | 26 | 75%
2025-07-01 | 430000 | 390000 | 40000 | 9.302% | 10 | 0 | 25 | 68%
2025-08-01 | 415000 | 385000 | 30000 | 7.229% | 9 | 1 | 25 | 65%
2025-09-01 | 505000 | 405000 | 100000 | 19.8% | 11 | 3 | 25 | 79%
2025-10-01 | 570000 | 440000 | 130000 | 22.81% | 14 | 3 | 26 | 84%
2025-11-01 | 595000 | 465000 | 130000 | 21.85% | 15 | 2 | 27 | 85%
2025-12-01 | 480000 | 420000 | 60000 | 12.5% | 12 | 1 | 26 | 70%
2026-01-01 | 510000 | 430000 | 80000 | 15.69% | 12 | 2 | 27 | 76%
2026-02-01 | 535000 | 440000 | 95000 | 17.76% | 13 | 1 | 27 | 78%
2026-03-01 | 560000 | 450000 | 110000 | 19.64% | 14 | 3 | 28 | 81%
TOTALS | 7505000 | 6225000 | 1280000
AVERAGES | 500333.3333 | 415000 |  | 16.6% | 11.8 | 1.8 | 25.7333 | 76.47%

## Staff Roster
Name | Department | Role | Location | Current Project | Allocation Pct | Billable Hours This Month | Utilization Target | Utilization Gap | Skills | Availability Next Month | Start Date | Notes
Eran Chen | Executive | Managing Principal | New York | Firm-wide / The Mira Hotel | 30% | 42 | 50% | -47.5% | Leadership; Client Relations; Design Direction | Available for new project oversight | 39156 | Splitting time across Mira Hotel pitch and firm management
Nile Lichtenstein | Executive | Principal | New York | Shore Club Residences | 40% | 56 | 50% | -30% | Leadership; Design Review; Client Relations | Limited - Shore Club CD push | 39965 | Leading Shore Club design vision through CD phase
Megumi Takata | Executive | Chief Operating Officer | New York | Operations | 10% | 14 | 25% | -65% | Operations; Finance; HR Oversight | Available | 40918 | Operational oversight; not project-billable
Akshay Mehra | Architecture | Project Architect | New York | Shore Club Residences | 100% | 148 | 85% | 8.824% | Revit; Bluebeam; Permit Coordination; Consultant Mgmt | Unavailable - Shore Club CD deadline | 42625 | OVERALLOCATED: working nights to meet 50% CD issuance
Yinxing Liu | Architecture | Design Team Lead | New York | Upstate Condo | 90% | 126 | 85% | -7.353% | Revit; Rhino; Team Management; Design Review | Partially available after DD milestone | 42114 | Also training junior staff on Revit workflows
Carlos Rivera | Architecture | Senior Designer | Fort Lauderdale | Shore Club Residences | 85% | 119 | 85% | -12.5% | Rhino; AutoCAD; SketchUp; Facade Design | Limited - CD phase | 43136 | Supporting facade documentation for Shore Club
Priya Narayanan | Architecture | BIM Manager | New York | Mayflower / Shore Club | 110% | 154 | 85% | 13.24% | Revit; BIM 360; Navisworks; Clash Detection | Unavailable | 43040 | OVERALLOCATED: split across two CD-phase projects
Sarah Kim | Architecture | Interior Designer | New York | Shore Club Residences / Riverside Tower | 95% | 133 | 85% | -2.206% | Interior Design; InDesign; Photoshop; Material Selection | Limited | 43696 | Interiors for Shore Club units and Riverside amenity spaces
David Okonkwo | Architecture | Project Manager | Fort Lauderdale | Shore Club Residences | 100% | 140 | 85% | 2.941% | Project Management; Scheduling; Budget Tracking | Unavailable | 43843 | Managing Shore Club construction admin coordination
Hannah Bergstrom | Architecture | Junior Designer | New York | Riverside Tower | 80% | 112 | 85% | -17.65% | Rhino; Grasshopper; SketchUp; Visualization | Available 20% | 45082 | Supporting DD drawings for Riverside Tower
Marco Vitale | Architecture | Facade Consultant | Remote | Shore Club / Mayflower | 100% | 140 | 85% | 2.941% | Facade Engineering; Waterproofing; Thermal Analysis | Unavailable | 44277 | Reviewing facade details across two active CD sets
Aisha Patel | Architecture | Sustainability Lead | New York | Jersey City Waterfront Tower | 60% | 84 | 85% | -38.24% | LEED; Energy Modeling; Sustainability Reporting | Available 40% for new SD project | 43599 | Early-stage sustainability framework for Jersey City
Tomoko Endo | Architecture | Urban Planner | New York | Jersey City Waterfront Tower | 75% | 105 | 85% | -22.79% | Urban Planning; Zoning Analysis; Site Planning | Available 25% | 44810 | Site planning and zoning research for Jersey City SD
Thanhthao Le | Architecture | Associate Team Leader | New York | The Mira Hotel & Residences | 90% | 126 | 85% | -7.353% | Visualization; Rhino; InDesign; Presentation Production | Limited - competition deadline | 43169 | Leading concept visualization for Dubai hospitality project
Keith Sagliocca | Architecture | Team Leader | New York | Mayflower | 95% | 133 | 85% | -2.206% | Bluebeam; Excel; Code Compliance; Consultant Coordination | Unavailable - CD deadline | 42969 | Coordinating Mayflower CD with city review submission
Michael Unsicker | Architecture | Principal | New York | The Mira Hotel / Hoboken Residential | 70% | 98 | 60% | 2.083% | Client Relations; Budgets; Scheduling; Excel | Available 30% | 41760 | Overseeing Mira Hotel concept and Hoboken DD
Joseph Kim | Architecture | Architect | New York | Jersey City Waterfront Tower / Competitions | 80% | 112 | 85% | -17.65% | Rhino; Claude; Grasshopper; Site Analysis; Visualization | Available 20% | 43784 | SD design and competition research
John Silver | Architecture | Designer | New York | Riverside Tower | 85% | 119 | 85% | -12.5% | Revit; AutoCAD; SketchUp; Rhino; BIM 360 | Limited | 43983 | Producing sections and 3D model for DD
Ryoko Okada | Interior | Principal Interior | New York | Shore Club / Hoboken Residential | 100% | 140 | 80% | 9.375% | Bluebeam; Photoshop; InDesign; Interior Specifications | Unavailable | 42614 | Reviewing interior markups across two projects
Lily Tran | Marketing | Marketing Manager | New York | Firm-wide |  |  |  |  | InDesign; Photoshop; RFP Assembly; PR Coordination | Available | 44105 | Award season - coordinating AIA and Architizer submissions
Derek Washington | Marketing | Graphic Designer | Remote | Firm-wide |  |  |  |  | InDesign; Illustrator; Photoshop; Presentation Design | Available | 44389 | Building RFP template system
Sofia Hernandez | Marketing | Content Strategist | New York | Firm-wide |  |  |  |  | Copywriting; Social Media; Website Content | Available | 44669 | Website refresh content development
Nina Kovalenko | Marketing | Social Media Coordinator | Remote | Firm-wide |  |  |  |  | Social Media; Content Calendar; Analytics | Available | 44935 | Managing Instagram and LinkedIn content
Thalia Morrison | Executive | Executive Assistant | New York | Executive Support |  |  |  |  | Outlook; Scheduling; Travel Planning; ZoomInfo | Available | 43276 | Supporting Eran Chen - travel season upcoming
Robert Flanagan | HR | HR Director | New York | HR Operations |  |  |  |  | Recruiting; Policy; Compliance; Benefits Admin | Available | 42415 | Overseeing onboarding for two new hires in April
Jessica Chu | HR | Recruiting Coordinator | New York | HR Operations |  |  |  |  | Recruiting; Interview Scheduling; Job Postings | Available | 44872 | Active searches: 2 junior designers + 1 project architect
Sam Petrov | Operations | Office Manager | New York | Office Operations |  |  |  |  | Facilities; Vendor Management; Office Systems | Available | 43535 | Coordinating new seating plan for April hires
Diana Reyes | Operations | IT Administrator | New York | IT Infrastructure |  |  |  |  | IT Admin; Software Licensing; Server Management | Available | 44067 | Revit license allocation and server maintenance
Kevin O'Brien | Operations | Finance Manager | New York | Finance |  |  |  |  | QuickBooks; Excel; Budgeting; Invoicing; Payroll | Available | 42885 | QuickBooks Desktop to Online migration underway
Fatima Al-Rashid | Operations | Procurement Specialist | Fort Lauderdale | Shore Club Residences |  |  |  |  | Procurement; Vendor Relations; Material Sourcing | Available | 44487 | Sourcing facade material samples for Shore Club
Ben Torres | Operations | Facilities Coordinator | New York | Office Operations |  |  |  |  | Facilities; Maintenance; Space Planning | Available | 45019 | Updating Illustrator seating chart for new hires
OPEN POSITION | Architecture | Junior Designer | New York | Riverside Tower | 0% | 0 | 85% | -100% | Rhino; SketchUp; Visualization | Start date: May 2026 |  | Interviewing candidates - need for DD support
OPEN POSITION | Architecture | Project Architect | Fort Lauderdale | TBD | 0% | 0 | 85% | -100% | Revit; Bluebeam; CD Experience; Permit Coordination | Start date: June 2026 |  | Need for growing Fort Lauderdale workload
TBD | Architecture | Intern | New York | TBD | 0% | 0 | 50% | -100% | Rhino; AutoCAD; Adobe Suite | Start date: Summer 2026 |  | Summer intern position
TBD | Marketing | Junior Marketing Coordinator | Remote | Firm-wide |  |  |  |  | Social Media; Content Writing; Canva | Available | 46174 | New marketing support role
TBD | Operations | Junior IT Support | New York | IT Infrastructure |  |  |  |  | IT Support; Help Desk; Network Admin | Available | 46204 | Growing IT needs
SUMMARY
Total Billable Hours | 2101
Average Allocation | 67.95%
Overallocated Staff Count | 1

## Project Portfolio
Project Name | Typology | Location | Phase | Contract Fee | Fee Method | Reimbursable Pct | Square Footage | Construction Cost Estimate | Hours Planned | Hours Actual | Hours Remaining | Hours Variance | Staff Assigned | Consultant Costs | Change Orders | Start Date | Target Completion
Shore Club Residences | Residential Condo | Fort Lauderdale FL | CD | 4200000 | Percentage | 12% | 385000 | 78000000 | 28000 | 31200 | -3200 | 11.43% | 8 | 1450000 | 3 | 45337 | 46235
Riverside Tower | Residential Rental | New York NY | DD | 3100000 | Time & Resources | 10% | 265000 | 52000000 | 22000 | 18500 | 3500 | -15.91% | 6 | 980000 | 1 | 45444 | 46341
Harbor View Residences | Residential Condo | Jersey City NJ | CA | 2800000 | Percentage | 15% | 210000 | 44000000 | 19000 | 20100 | -1100 | 5.789% | 5 | 870000 | 4 | 44936 | 46021
Wynwood Arts Mixed-Use | Mixed-Use | Miami FL | CA | 3500000 | Fixed Fee | 10% | 295000 | 61000000 | 24000 | 23800 | 200 | -0.8333% | 7 | 1120000 | 2 | 45005 | 45915
Jersey City Waterfront Tower | Residential Condo | Jersey City NJ | SD | 2400000 | Percentage | 12% | 225000 | 47000000 | 16000 | 4200 | 11800 | -73.75% | 4 | 340000 | 0 | 45901 | 46813
Hoboken Residential | Residential Rental | Hoboken NJ | DD | 1800000 | Time & Resources | 10% | 142000 | 29500000 | 14000 | 9800 | 4200 | -30% | 4 | 520000 | 1 | 45597 | 46402
The Mira Hotel & Residences | Hospitality | Dubai UAE | SD | 5600000 | Percentage | 15% | 410000 | 125000000 | 35000 | 8900 | 26100 | -74.57% | 6 | 680000 | 0 | 45823 | 47119
Upstate Condo | Residential Condo | Hudson Valley NY | DD | 1950000 | Fixed Fee | 10% | 168000 | 34000000 | 15000 | 11200 | 3800 | -25.33% | 5 | 610000 | 2 | 45505 | 46478
Fort Lauderdale Cultural Center | Cultural | Fort Lauderdale FL | CA | 2200000 | Percentage | 12% | 88000 | 22000000 | 17000 | 17600 | -600 | 3.529% | 4 | 540000 | 1 | 44805 | 45838
Mayflower | Residential Condo | New York NY | CD | 3800000 | Time & Resources | 12% | 310000 | 64000000 | 26000 | 24100 | 1900 | -7.308% | 7 | 1280000 | 2 | 45245 | 46143
TOTALS |  |  |  | 31350000 |  |  | 2498000 | 556500000 | 216000 | 169400 |  |  | 56 | 8390000 | 16

## Financial Summary
Metric | Value | Notes
Total Revenue (15 months) | 7505000 | Sum of all monthly revenue
Total Expenses (15 months) | 6225000 | Sum of all monthly expenses
Total Net Profit (15 months) | 1280000 | Revenue minus expenses over period
Average Monthly Revenue | 500333.3333 | Mean monthly revenue
Average Monthly Expenses | 41500000% | Mean monthly expenses
Average Profit Margin | 0.16601 | Mean profit margin percentage
Highest Revenue Month | 595000 | Peak monthly revenue
Lowest Revenue Month | 415000 | Lowest monthly revenue
Revenue Volatility | 53773.1862 | Standard deviation of revenue
Total Active Projects (Latest) | 14 | Projects active in Mar 2026
Total Commissions (15 months) | 27 | Total new projects won
Current Staff Count | 2800% | Staff headcount as of Mar 2026
Average Utilization Rate | 76.47% | Mean staff utilization percentage

## Project Dashboard
Metric | Value | Notes | Phase | Count
Total Portfolio Value | 31350000 | Sum of all contract fees | SD | 2
Average Contract Fee | 3135000 | Mean project fee | DD | 3
Largest Project Fee | 5600000 | Highest contract value | CD | 2
Total Construction Cost | 556500000 | Sum of estimated construction costs | CA | 3
Total Square Footage | 2498000 | Total building area across portfolio
Average SF per Project | 249800 | Mean project size
Total Hours Planned | 216000 | Budgeted hours across all projects
Total Hours Actual | 16940000% | Hours spent to date
Overall Hours Variance | -0.21574 | Portfolio-level hours performance
Total Staff Assigned | 56 | Staff allocated to projects
Total Consultant Costs | 8390000 | External consultant expenses
Total Change Orders | 16 | Change orders issued
Projects in SD | 2 | Schematic Design phase
Projects in DD | 3 | Design Development phase
Projects in CD | 2 | Construction Documents phase
Projects in CA | 3 | Construction Administration phase
Projects Over Budget (hours) | 3 | Projects exceeding planned hours

## Sources
Title | URL
oda-monthly-financials.csv | https://advai-my.sharepoint.com/personal/noam_advas_ai/_layouts/15/Doc.aspx?sourcedoc=%7B0387F033-9C6E-487E-B82C-A8E3E11CBE36%7D&file=oda-monthly-financials.csv&action=default&mobileredirect=true
ODA-Resource-Allocation.xlsx | https://advai-my.sharepoint.com/personal/noam_advas_ai/_layouts/15/Doc.aspx?sourcedoc=%7B9797469E-5A40-480A-8ECC-138FF42CFE28%7D&file=ODA-Resource-Allocation.xlsx&action=default&mobileredirect=true&DefaultItemOpen=1
oda-project-tracking.csv | https://advai-my.sharepoint.com/personal/noam_advas_ai/_layouts/15/Doc.aspx?sourcedoc=%7B9105F584-62EA-43BE-AA7D-8315CACC7160%7D&file=oda-project-tracking.csv&action=default&mobileredirect=true