## Data
ODA Project Tracking
Converted from oda-project-tracking.csv
Project_Name | Typology | Location | Phase | Contract_Fee | Fee_Method | Reimbursable_Pct | Square_Footage | Construction_Cost_Estimate | Hours_Planned | Hours_Actual | Staff_Assigned | Consultant_Costs | Change_Orders | Start_Date | Target_Completion
Shore Club Residences | Residential Condo | Fort Lauderdale FL | CD | 4200000 | Percentage | 12% | 385000 | 78000000 | 28000 | 31200 | 8 | 1450000 | 3 | 2024-02-15 | 2026-08-01
Riverside Tower | Residential Rental | New York NY | DD | 3100000 | Time & Resources | 10% | 265000 | 52000000 | 22000 | 18500 | 6 | 980000 | 1 | 2024-06-01 | 2026-11-15
Harbor View Residences | Residential Condo | Jersey City NJ | CA | 2800000 | Percentage | 15% | 210000 | 44000000 | 19000 | 20100 | 5 | 870000 | 4 | 2023-01-10 | 2025-12-30
Wynwood Arts Mixed-Use | Mixed-Use | Miami FL | CA | 3500000 | Fixed Fee | 10% | 295000 | 61000000 | 24000 | 23800 | 7 | 1120000 | 2 | 2023-03-20 | 2025-09-15
Jersey City Waterfront Tower | Residential Condo | Jersey City NJ | SD | 2400000 | Percentage | 12% | 225000 | 47000000 | 16000 | 4200 | 4 | 340000 | 0 | 2025-09-01 | 2028-03-01
Hoboken Residential | Residential Rental | Hoboken NJ | DD | 1800000 | Time & Resources | 10% | 142000 | 29500000 | 14000 | 9800 | 4 | 520000 | 1 | 2024-11-01 | 2027-01-15
The Mira Hotel & Residences | Hospitality | Dubai UAE | SD | 5600000 | Percentage | 15% | 410000 | 125000000 | 35000 | 8900 | 6 | 680000 | 0 | 2025-06-15 | 2029-01-01
Upstate Condo | Residential Condo | Hudson Valley NY | DD | 1950000 | Fixed Fee | 10% | 168000 | 34000000 | 15000 | 11200 | 5 | 610000 | 2 | 2024-08-01 | 2027-04-01
Fort Lauderdale Cultural Center | Cultural | Fort Lauderdale FL | CA | 2200000 | Percentage | 12% | 88000 | 22000000 | 17000 | 17600 | 4 | 540000 | 1 | 2022-09-01 | 2025-06-30
Mayflower | Residential Condo | New York NY | CD | 3800000 | Time & Resources | 12% | 310000 | 64000000 | 26000 | 24100 | 7 | 1280000 | 2 | 2023-11-15 | 2026-05-01

## Notes
ODA Spreadsheet Notes
Generated by Copilot – styled for ODA reporting
This workbook contains the source data converted from CSV and formatted with ODA-style headers, tables, and number formats.